## Work Plan
ANNUAL MWEITI WORK PLAN 2016
Objectives | EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Costs in USD |  |  | Challenges and Obstacles
[7 empty] | 2015/2016 | 2016/2017 | 2017/2018
1) EITI-compliant status achieved. | all requirements | Official launch of MWEITI implementation | 1.7 EITI launched | Renew commitment of government, companies and CSO to EITI implementation | National Secretariat | 2016-09-30 | 30000 |  |  | Lack of awareness of EITI beyond core group of previous EITI task force
| all requirements | National Secretariat set up and opertaions | 1.9 Formation of EITI Secretariat based in the MoF | EITI Champion and MSG are supported | National Secretariat | 2016-06-30 | 313850 | 296920 | 268867.4 | Open one account for the Secretariat from different donors. ensuring that resources are earmarked to support EITI for three years.Ensuring smooth cashflow for the project.
| all requirements | Coordination and pledging round with international partners, including World Bank, AfDB, EU, BMZ/GIZ, DFID, Royal Norwegian Embassy, private foundations. | 1.12 Donor support earmarked and committed | Effective international cooperation | National Secretariat | On going | in-kind ($5,000)
| requirements 3 - 5 | Legal and practical obstacles to implementation: research and identify any legal, regulatory or other practical obstacles that may hinder or prevent the implementation of the EITI process and reporting. | 1.13 Legal and practical obstacles study conducted | Provide direction to the MSG on necessary steps to take to address legal and practical obstacles | National Secretariat | 2017-06-30 | 20000 |  |  | Legislative and legal barriers – The EITI process may be hampered by laws or contractual agreements between the government and private companies
|  | Policy and legislation for EITI: scoping research, consultations and drafting of policy and legislation. | 1.14 Policy and legislation produced | Provide legislative framework for implementation of the EITI | National Secretariat, MSG, Ministry of Justice | 2017-12-30 | 40000 | 40000
|  | Scope of EITI implementation: research and identify which natural resources, revenue/payment streams, companies and state authorities should be included in the EITI reports. | 1.15 Scope of EITI implementation defined | Provide direction to the MSG on the scope for the EITI implementation and reporting | National Secretariat | 2016-04-30 | 60000
| requirement 5.2 | Preparatory Reporting Template drafted for Independent Administrator (Reconciler) | 1.16 Preparatory Reporting Template produced | Readiness to prepare 1st MWEITI report | National Secretariat, MSG | 2016-06-30 | in-kind ($1,000)
| requirement 5.2 | TOR for Independent Administrator (Reconciler) approved by MSG, including decision of materiality threshold. | 1.17 ToR for Independent Administrator (Reconciler) developed | Ensured that reconciliation is carried out thoroughly and Independent Administrator understand role | National Secretariat, RBM, NAO | 01 May 2016 and subsequent years | 2000
| requirement 5.2 | Independent Administrator (Reconciler) is contracted. Procurement started in a timely manner (6-9 months, MoF). | 1.18 Independent Administrator contracted | Confidence with stakeholders on the integrity of EITI is increased | MoF, National Secretariat | 31 January 2016 and subsequent years | 60000 |  | 70000
| requirement 3.1; requirement 3.2.; requirement 3.3; requirement 3.4; requirement 3.5; | MSG committee on contextual information makes sure that resource persons from relevant government agencies provide information. | 1.19 Contextual information collected | Maximise synergies between stakeholders | National Secretariat, MSG | 2016-02-01 | 5000 | 10000 | 10000 | Information is currently not consolidated and is published though a variety of means and agencies
| requirement 5.2 | Independent Administrator (Reconciler) to collect information from government and companies for reconciliation, and drafting of report. | 1.20 Report produced | Independent third party reconciliation will add weight to the tax payment figures put into the public domain | National Secretariat | 2016-09-30
| requirements 5.3 and 6 | MSG endorses first EITI report | 1.21 First EITI report endorsed | Public debate on Malawi extractive industries is better informed | MSG | 31 December 2016 (tbd) | 2500
|  | MSG publishes the first EITI report | 1.22 First EITI report published | Public debate on Malawi extractive industries is better informed | MSG | 31 December 2016 (tbd) |  | 20000
| requirements 5.3 and 6 | MSG endorses second EITI report | 1.23 Second EITI report endorsed | Public debate on Malawi extractive industries is better informed | MSG | 31 December 2017 (tbd) |  | 2500
|  | MSG publishes second EITI report | 1.24 Second EITI report published | Public debate on Malawi extractive industries is better informed | MSG | 31 December 2017 (tbd) |  |  | 20000
| requirement 7.1 | Identify, investigate and address the cause of discrepancies in reconciliation and consider recommendations for improvement from the Independent Administrator. | 1.23 Findings consolidated and submitted to government | Governance of the extractives sector in Malawi is improved | MSG | 30 November 2016 (tbd) and subsequent years |  | 5000
| requirements 1.3 and 7.2 | Research and present information on the recent activities | 1.24 Annual Activity Report 2015/2016 | Confidence with stakeholders on the results of EITI is increased | National Secretariat | 30 June 2016 |  | 5000
| requirements 1.3 and 7.2 | Research and present information on the recent activities | 1.25 Annual Activity Report 2016/2017 | Confidence with stakeholders on the results of EITI is increased | National Secretariat | 30 June 2017 |  |  | 5000
| requirement 1.6 b) and The Validation Guide | Undergo independent validation for EITI compliance | 1.26 Assessment of EITI implementation in MW | MW reaches compliant status | National Secretariat | 15 December 2017 |  |  |  | EITI International Secretariat is responsible for covering costs and arrangements for the independent validation
| all requirements | Inform policy and legal reforms in accordance with Africa Mining Vision (AMV), e.g. Mines and Minerals Act, Taxation Act | 2.1 Harmonised policy and legal framework for investors | Ease of doing business is improved for higher quality investments | MoF, National Secretariat | 15 December 2017 |  |  |  | Policy coherence both within Malawi and SADC/AU
2) The MSG forms and strengthens partnerships between government/administration, companies and public for attracting quality investments. | all requirements | Checklist for licence and contract awarding government agencies concerning the due diligence of investors | 2.2 Due diligence checklist developed | Resilient legal and contractual frameworks for mutual benefit in place | National Secretariat | 2016-11-30 |  | 2000 | 2000
| requirement 3.11 | The beneficial owners of corporate entities that bid for, operate, or invest in extractive assets will be made publicly available on the government website/website of MWEITI in accordance with Requirement 3.11 | 2.3 Beneficial ownership information published | The public and government's understanding of and trust in MW investors are increased | National Secretariat | 2016-09-30 | 5000 | 30000 | 7500
| requirement 3.12 | Contract and licences are publicly disclosed on the government website/website of MWEITI in accordance with Requirement 3.12 | 2.4 Contracts and licences are disclosed online | Improve mutual trust and good governance in Malawi's extractive industries | National Secretariat | 2016-09-30 |  | 5000 |  | 1 Development Agreement (DA) has been awarded by Government, which has subsequently been disclosed. Thus there is currently actual contract transparency in the sector.
| all requirements | MSG visit to mine sites to strengthen partnerships and technical knowledge and competence of members. | 2.5 Visit to mines in Malawi conducted | Improve mutual trust and good governance in Malawi's extractive industries | National Secretariat, MSG | 2016-09-30 |  | 15000
| all requirements | Participation in EITI Global Conference (Lima, Peru) (participation of at least 6 people from Secretariat and MSG) | 2.6 Participation in EITI Global Conference | The MSG stakeholders and the constituencies they represent share knowledge and present Malawi's achievements, building MSG trust and public's understanding of MWEITI | MSG | 2016-02-28 |  | 60000
| requirement 7 | One report is submitted to the MSG on fiscal regime and socio-economic impacts with gender disaggregated data (sector-wide situation and risk analysis) along the decision/value chain in the extractives sector. | 3.1 Decision/value chain in the extractives sector in terms of revenue management and benefits for the people is assessed. | Provides direction to the MSG in what positive and negative results MWEITI should focus on. | MoF, National Secretariat | 31 March 2016 |  | 15000
3) Increased revenue base and socio-economic impacts from extractive industries. | requirements 1.3 and 7 | Conduct community meetings to discuss revenue and non-revenue issues affecting communities in mining areas. Assign EITI focal points in mining areas, e.g. members of district assemblies or local administrations. | 3.2 Institutionalised dialogue of national government, local governments, companies and local communities is assessed and improved | Participatory multi-stakeholder process strengthened. | ActionAid Malawi, National Secretariat | 31 May 2016 |  | 20000
| requirements 1.3 and 7 | Measure the effect of MWEITI on the level of trust in the extractives sector, representative, quantitative and scientifically robust survey sets baseline before starting with MWEITI - same survey conducted after 1st EITI report; e.g. relations state authorities / citizen, state authorities / chiefs, state authorities / companies, companies / chiefs, companies / citizens, chiefs / citizens, CSOs / citizens; parliamentarians, media, gender-disaggregated. | 4.1 Baseline and mid-term assessment of stakeholder trust conducted | Impact of EITI on trust of stakeholders in the extractive industries is fully understood | National Secretariat | 2015-09-01 | 20000 |  | 20000
4) Strengthened trust among stakeholders of natural resource management. | requirement 1.3 g) | Form a Committee on Communication & Engagement | 4.2 Committee formed | Find and maximise audience of MWEITI report | National Secretariat, Ministry Natural Resources, Energy and Mining, CFJ, ActionAid Malawi, Paladin Africa Ltd., Bwanje Cement Company Limited | 2016-10-31 | 2500 |  |  | Some lack of cooperation / mistrust among stakeholders - Different stakeholder groups have different visions or reasons for pursuing EITI membership which, if not managed well, can lead to low levels of cooperation
| requirement 1.3 g) | Fully costed Communication and Engagement Strategy and Workplan is drafted for endorsement by MSG | 4.3 Communication and Engagement Strategy and Workplan drafted and endorsed by MSG | Find and maximise audience of MWEITI report | MSG | 31 January 2016 | 20000 |  |  | Lack of awareness of EITI beyond core group of previous EITI task force
| requirement 1.3 g) | Ensure that Communication and Engagement Strategy and Workplan is implemented and e.g. MWEITI website is developed and updated in a timely manner to provide relevant information, messages from EITI generated data are customised (content, format, channel) for target groups; conduct outreach and capacity building activities with targeted stakeholders; involvement and mobilisation capacities of stakeholders beyond the MSG members. | 4.4 Communication and Engagement Strategy and Workplan implemented | Factual and valuable information provided to stakeholders leading to increased understanding and awareness of MWEITI generated data | National Secretariat, Media House and Committee on Communication and Engagement | 31 December 2017 | 100000 | 150000 | 150000 | Scepticism toward EITI - Some local stakeholders raise questions about the wisdom or necessity of joining EITI
Total | [6 empty] | 680850 | 676420 | 553367.4 | 1910637.4
Note on C9: This activity (1.14 Policy and legislation produced) will be linked or carried out in conjunction with the previous one (1.13 Legal and practical obstacles study conducted)
Note on C15: This is included for tracking purposes but is budgeted under 1.18 Independent Administrator contracted.
Note on C20: The MSG will work hand-in-hand with the Independent Administrator and follow up on discrepancies and reasons for these.
Note on C24: MSG and the National Secretariat to examine AMV and Malawi's legislative and regulatory framework within the MSG meetings and create a sub-grouping to provide information on Malawi's status.
Note on H5: One-day launch of EITI in Lilongwe with media coverage and logistics for stakeholders from across the country.
Note on H6: See separate budget for the National Secretariat for a breakdown of these costs.
Note on H8: Consultancy fees and logistics
Note on H9: Consultancy fee including consultation with stakeholders and drafting of legislation
Note on H10: This includes consultancy fees (for international and national consultants), logistics and consultations with stakeholders.
Note on H11: The MSG will produce the initial template for the Reconciler.
Note on H13: Based on average costs for EITI approved Independent Administrator.
Note on H16: Meeting logistics (based on precedent). Two MSG members not based in Lilongwe.
Note on H26: Preliminary desk study to inform consultancy ToRs and consultation with stakeholders
Note on H32: Based on cost for similar studies.
Note on H34: Based on competitive cost for similar strategy development.
Note on H35: This includes first year implementation of Communications and Advocacy Strategy and Workplan (developed under 4.3): website design and hosting, information, education and communication materials, using different media to raise awareness and understanding and build trust (radio, TV, online)
Note on I17: Based on average printing costs in Malawi for high quality, colour report.
Note on I18: Meeting logistics (based on precedent). Two MSG members not based in Lilongwe.
Note on I21: Costs covers logistics and printing of now more than 100 reports.
Note on I25: Logistics for consultations with relevant stakeholders.
Note on I26: Consultancy fees to investigate beneficial owners and collect datas.
Note on I27: Design and maintenance cost for webpage
Note on I29: Travel, logistics and promotional material.
Note on I30: Based on competitive cost for similar studies.
Note on I31: Meetings to cover all regions.
Note on J19: Based on average printing costs in Malawi for high quality, colour report.
Note on J22: Costs covers logistics and printing of now more than 100 reports.
Note on J25: Logistics for consultations with relevant stakeholders.
Note on J26: Ongoing data collection and disemination
Note on J32: Based on cost for similar studies.